## Sheet1
ID | Risk Description | Likelihood | Impact | Risk Score | Mitigation | Status
1 | Incorrect IP addressing | 3 | 4 | 12 | It is needed to follow thestudent ID rule, double-check subnets | Open / Sreelakshmi
2 | Cloud cost exceeds budget | 2 | 5 | 10 | It is needed to use cost calculators, monitor usage | Open / Sahithi
3 | Network diagram errors | 3 | 3 | 9 | It is needed to do the peer review diagrams before submission | Open / Sahithi
4 | Security vulnerabilities in setup | 4 | 5 | 20 | It is needed to apply recommended controls, follow best practices | Open / Sreelakshmi
5 | GitHub repository inconsistent | 2 | 3 | 6 | It is needed to assign commits per member, check folder structure | Open / Both